## Impact Assessment
CHANGE IMPACT ANALYSIS TEMPLATE
PROJECT TITLE | Bug Identification |  |  | DATE CREATED | 17/11/2020
ORGANIZATION | Conestoga College |  |  | VERSION | 17/11/2020
PRIMARY CONTACT | Srdjan Manojlovic |  |  | PREPARED BY ORG. | VSN
PROJECT DESCRIPTION | Cilent has become aware of the bug in the existing SharePoint 2013 platform.As a result,department data has had incorrect permission for the past 12 months. |  |  | KEY SPONSOR | Conestoga College
|  |  |  | PRODUCT OWNER | Conestoga College
|  |  |  | BUSINESS ANALYST | Kartik velede
|  |  |  | BUSINESS ANALYST | Kartik velede
STATUS | Active |  |  | APPROVED BY | Srdjan Manojlovic
STATE OF EVENT / ACTION / STRATEGY
CURRENT STATE | Due the bugs in the SharePOint 2013 platform,all the data which is present it that had incorrect permission which could lead to data breaches
RESULTING STATE POST-CHANGE | After bug is fixed alll the incorrect permission were rectified and data is protected from the breaches
GAP BETWEEN CURRENT STATE AND CHANGE COMPLETION | A solution was identiied to fix the bug that is leading to inorrect data permisssions
KEY RISKS | The followings are some of the risks identified data interdrity ,data confidentaility ,corruption of database and theft of intellectual property
IMPACT OVERVIEW
SUMMARY OF IMPACT
overall, due the bugs that were identifiend in the platform, the project which is ongoing has effteced has many changes needs to be done to ongoing project which will inturn effect the deadline and also few data breaches were observed.
IMPACT TYPE |  | IMPACT TIMELINE |  | IMPACT LEVEL
Critical |  | 12 months |  | High
POSITIONS/tASKS AFFECTED |  |  | NUMBER AFFECTED
Project Migration |  |  | 1
Project deadline |  |  | 2
Allotment of permissions |  |  | 3
CHANGE REQUEST
CR ID: | 13245
TITLE | Bug detection Fixed
DESCRIPTION | The bug which creadted incorrect permission to department data is fixed
EVALUATOR | Srdjan Manojvalic
DATE PREPARED | 17/11/2020
EST. TOTAL EFFORT | Relevant Bug detection
EST. SCHEDULE IMPACT | 12 Month
ADDITIONAL COST IMPACT | 30000
QUALITY IMPACT | Data confidentality imprved
OTHER COMPONENTS AFFECTED | The process of migration gets affetced
OTHER TASKS AFFECTED | Allotment of permissions
LIFE-CYCLE COST ISSUES | The life cycle process willl be changed silghthly The timeline increase ,so as the cost will aslo increase
STATUS | Completed
CHANGE REQUIREMENTS
COMMUNICATION | All the users in the organization needs to be communicated about the changes which are made and impact thathas had caused to make these changes
TRAINING | The trainig manual needs to be modified according to the changes that are made
LEADERSHIP | Leadership team needs to the initiative in implementing the chnages that were made
STAKEHOLDER COLLABORATION / COMMUNICATION | The cilent needs to be communicated about the bug fix and all the changes that were made.