## Slide 1: Meeting with Stakeholder
Submitted By-
Sukhjeevan Kaur (8672788)
Dhruvi Amin (8683008)
Karthik Velede (8672807)
Amrit Pal Singh (8681749)

## Slide 2
Project Status Update
Scrum Master: Kartik Velede
Accomplishments: Requirement Gathering Business Proposal Elicitation and analyses of the requirement Plan and Design Capturing Wireframe and Site structure BRD Implementation of proposed solution Key Issues Incorrect Permission due to software bug. Budgeting and report department must remain on premise and not migrate to cloud.
Schedule | Base | Due | r
Project Management |  |  | 
Analyze and reviewed tracking log | 18/11/2020 | 23/11/2020 | G
Scheduling, timing and work effort | 19/11/2020 | 22/11/2020 | G
Previous | G | Current | G
Actions | Responsible | Due | Status
Final Working Deliverable | Sukhjeevan Kaur | 12/15/2020 | G
Written Summary of completed | Karthik Velede | 12/15/2020 | G
Written Instructions of project works | Amrit Pal Singh | 12/15/2020 | G
Handoff plan | Dhruvi Amin | 12/15/2020 | G
N | R | A | G | C

## Slide 3: Bug Detection Resolution
Firstly ,analysis is done on the Existing platform to identify the software Bug ,after detecting the bug which causing the incorrect permission to department data .All the data which has been exposed to Breach will be reviewed and confidentiality to data is provided by changing the passwords.

## Slide 4: Software Depreciation Resolution
As of December 1 the SharePoint Migration tool will no longer receive feature so security updates. We must use another Migration tools like Sharegate and PowerShell for migration which will increase the security and cost will be increased in initial stage but in long term the maintenance cost will be reduced.

## Slide 5: Change in Requirement Resolution
We will remove the budgeting and reporting department from the SharePoint Online. As we have not made any changes in SharePoint 2013 so no changes will be done on SharePoint 2013.Moreover this will push the deadline for this project.

## Slide 6: Not enough Resources Resolution
A change request will be created which involves downsizing the team working on the project by two. It will also involve a rescheduling of the timeline and task distribution of the project among the remaining members of the project team. There will also be an extension requested to the project completion date by 2 weeks.