## Sheet1
Task Name | Responsible | Duration (Days) | Start Date | Finish Date
Requriement gathering | Busniess analyst | 1 | 22-09-2019 | 23-09-2019
Documentation of Requriment specfication | Business analyst | 2 | 24-09-2019 | 26-09-2019
Planning the Migration | Business analyst | 2 | 24-09-2019 | 26-09-2019
Choose the service plan | Business analyst | 1 | 27-09-2019 | 28-09-2019
Signup of the service | IT head(Global admin) | 1 | 02-10-2019 | 03-10-2019
Validate the registration | IT head(Global admin) | 1 | 02-10-2020 | 03-10-2020
Add your Domain | IT head(Global admin) | 1 | 02-10-2019 | 03-10-2019
Validate the Domain | IT head(Global admin) | 1 | 02-10-2019 | 03-10-2020
Add users | IT head(Global admin) | 1 | 03-10-2019 | 04-10-2019
Validating the user creation | Employee of the organization(user) | 1 | 03-10-2019 | 04-10-2020
Add groups | IT head(Global admin) | 1 | 03-10-2019 | 04-10-2020
Add users to groups | IT head(Global admin) | 1 | 03-10-2019 | 04-10-2021
Assign roles to users | IT head(Global admin) | 1 | 03-10-2019 | 04-10-2022
Install apps | Employee of the organization(user) | 1 | 05-10-2019 | 06-10-2019
Configure outlook | Employee of the organization(user) | 1 | 05-10-2019 | 06-10-2019
Data Migration | Sharepoint admin | 4 | 03-10-2019 | 07-10-2019
Email Migration | Exchange admin | 4 | 03-10-2019 | 07-10-2019